SAP S/4HANA

Support Package Stack (SPS) Update

Complete Step-by-Step Procedure using Software Update Manager (SUM)

| Document Type | Technical Maintenance & Patching Guide |
| --- | --- |
| Component | SAP S/4HANA Application (ABAP Stack) |
| Scope | Support Package Stack (SPS) Update |
| Update Path | SAP S/4HANA 2023 SPS01 → SPS02 (example; applies to all SPS) |
| Update Tool | Software Update Manager (SUM) 2.0 |
| Instance Types | ASCS, ERS, PAS, AAS (ABAP Central System) |
| DB Platform | SAP HANA 2.0 SPS07+ (ABAP+HANA landscape) |
| OS | SLES 15 SP4 / RHEL 8.x for SAP (Linux) |
| SAP Notes | 2502552, 2209025, 2190195, 1680045, 2399707 |
| Prepared By | M2 Partnering Solution SAP Consulting |
| Date | March 2026 |
| Version | 1.0 |

# 1. Overview & Background

An SAP S/4HANA Support Package Stack (SPS) update is a major ABAP-layer maintenance event that applies a cumulative set of SAP corrections, enhancements, and new features to the application server. Unlike a simple kernel update (which replaces OS-level binaries), an SPS update imports thousands of ABAP objects, database table changes, activation programs, and configuration settings using the Software Update Manager (SUM).

SUM orchestrates the entire update lifecycle — from initial pre-checks and shadow repository creation through the actual import, activation, and post-processing phases. Most of the SUM execution happens in the 'uptime' phase while users can still work; only the final import and activation steps require a downtime window.

## 1.1  SPS vs Other Update Types

| Update Type | Tool | Downtime | Scope |
| --- | --- | --- | --- |
| SAP Kernel Update | OS file copy | 30–90 min | Binary executables only; no ABAP/DB change |
| SAP Note (SNOTE) | SNOTE / SPAM | None / minimal | Single corrections; few objects |
| Support Package (SP) | SPAM | 2–6 hours | Single component corrections; cumulative |
| Support Package Stack (SPS) | SUM 2.0 | 4–12 hours | All components updated together; new features included |
| SPS + Kernel (combined) | SUM 2.0 + OS copy | 4–12 hours | Full stack update: ABAP + kernel in one window |
| Release Upgrade (e.g., 2022→2023) | SUM DMO | 8–48 hours | Full system conversion; DB migration possible |

## 1.2  S/4HANA SPS Release Cadence

| Concept | Example | Notes |
| --- | --- | --- |
| S/4HANA Release | S/4HANA 2023 | Annual major release; new functional scope and platform capabilities |
| SPS (Support Package Stack) | SPS01, SPS02 | Cumulative corrections + features on top of the release; ~2 per year |
| FPS (Feature Package Stack) | FPS01 | Feature-only SPS shipped between SPS releases (some releases only) |
| Initial Shipment Stack | ISS | The base release without any SPS applied; not suitable for production |
| Recommended Stack | Maintenance Planner | SAP-generated consistent stack for kernel + ABAP + DB across components |

📌 NOTE: Always use SAP Maintenance Planner (https://apps.support.sap.com/sap/support/mp) to generate the target stack XML and download list. This ensures all components (ABAP, Kernel, HANA client) are at consistent, tested versions.

## 1.3  SUM Update Architecture

SUM 2.0 executes the SPS update in two major phases:

| Phase | User Impact | Activities Performed |
| --- | --- | --- |
| Preparation (Uptime) | System running normally | SUM pre-checks, shadow repository import, ABAP activation in shadow, preparation steps — system fully available |
| Configuration (Uptime) | System running normally | SUM downloads packages, validates stack, runs pre-downtime checks and conflict resolution |
| Shadow Import (Uptime) | System running normally | DDIC objects imported to shadow schema; ABAP programs compiled but NOT yet active — no impact to production |
| Pre-Downtime (Uptime) | System running normally | SUM completes as much import as possible before downtime to minimize actual downtime window |
| DOWNTIME Begin | System locked – no access | SUM locks system; final delta import; switches to new software version; activates DDIC and programs |
| Post-Processing | System coming up | Conversion programs run; background jobs for data migration; system handed over for testing |

## 1.4  Key SAP Notes

| SAP Note | Description |
| --- | --- |
| 2502552 | SAP S/4HANA – SUM-based update guide (master reference for SPS updates) |
| 2209025 | Software Update Manager 2.0 – prerequisites and installation guide |
| 2190195 | SUM 2.0 ABAP – known issues and corrections (check before every SUM run) |
| 2399707 | SUM prerequisite notes — OSS notes required before SUM execution |
| 1680045 | OS compatibility matrix for SAP kernel during SPS update |
| 2861952 | Recommended SUM and SP stack for S/4HANA 2023 |
| 2578458 | SUM: Near-Zero Downtime (nZDT) option for SPS updates |
| 3045229 | S/4HANA 2023 – mandatory corrections before SPS update |
| 2936831 | ABAP Test Cockpit (ATC) mandatory checks before SPS update |
| 2180923 | Simplification Item Catalog for S/4HANA SPS updates |

# 2. Prerequisites & Pre-Update Planning

## 2.1  SAP Maintenance Planner — Generate Target Stack

The SAP Maintenance Planner is the mandatory starting point for every SPS update. It generates a consistent stack XML file that SUM uses to determine which packages to download and apply.

- Log in to https://apps.support.sap.com/sap/support/mp

- Select 'Plan a New Maintenance Transaction'

- Choose your S/4HANA system from the LMDB or enter SID/product version manually

- Set target: S/4HANA 2023 SPS02 (or your target SPS level)

- Maintenance Planner generates a stack XML file and a download basket list

- Download ALL packages listed (ABAP SPs, Kernel, HANA Client, IGS, etc.)

- Save the stack XML file (STACK.XML) — SUM will need this to start

## 2.2  System Landscape & Version Assessment

| Check | Transaction / Command | Purpose |
| --- | --- | --- |
| Current S/4HANA SPS level | SM51 → Release Notes OR SE16N → CVERS | Confirm exact current SPS and SP level |
| Installed add-ons and industry solutions | SAINT → Installed packages | Check add-on compatibility with target SPS |
| Installed business functions | SFW5 | Verify no incompatible BFs for target SPS |
| Current SUM version installed | /usr/sap/<SID>/SUM/abap/SAPup -version | SUM must be 2.0 SP17+ for S/4HANA 2023 |
| System profile parameters | RZ10 / RZ11 | Note current profiles; SUM may add parameters |
| Active RFC destinations | SM59 | Some RFCs need disabling during SUM run |
| Custom namespaces | SE03 → Namespaces | Custom NS objects may conflict with SPS objects |
| Open transports in import queue | STMS | All imports must be complete before SUM start |
| Database statistics | DBACOCKPIT / HANA Cockpit | Fresh statistics help SUM query optimization |
| Available disk space | df -h /usr/sap /hana/shared /tmp | SUM needs 50+ GB depending on system size |

## 2.3  Download & Stage Support Packages

Download all packages identified by Maintenance Planner to a dedicated staging directory on the application server:

# Create staging directory

mkdir -p /usr/sap/<SID>/SUM/download

chown <sid>adm:sapsys /usr/sap/<SID>/SUM/download

# Verify downloaded packages (check against Maintenance Planner list)

ls -lh /usr/sap/<SID>/SUM/download/*.SAR

ls -lh /usr/sap/<SID>/SUM/download/*.ZIP

ls -lh /usr/sap/<SID>/SUM/download/STACK.XML

# Verify checksums vs SAP Software Center

md5sum /usr/sap/<SID>/SUM/download/*.SAR > /tmp/download_checksums.txt

cat /tmp/download_checksums.txt

## 2.4  SUM 2.0 Installation / Upgrade

SUM itself must be at the latest version before starting. If SUM is already installed from a previous update, upgrade it first:

# Check current SUM version

ls /usr/sap/<SID>/SUM/abap/SAPup

/usr/sap/<SID>/SUM/abap/SAPup -version 2>&1

# Extract new SUM from downloaded SAR (if upgrading SUM)

su - <sid>adm

mkdir -p /usr/sap/<SID>/SUM

cd /usr/sap/<SID>/SUM

SAPCAR -xvf /usr/sap/<SID>/SUM/download/SUM20SP<XX>_0.SAR

# Verify SUM extracted

ls /usr/sap/<SID>/SUM/abap/

# Must contain: SAPup, sumstart, abap/ directory

## 2.5  Pre-Update Mandatory Activities

| # | Task | Transaction | Status |
| --- | --- | --- | --- |
| 1 | Apply all mandatory prerequisite OSS Notes (SAP Note 2399707) | SNOTE |  |
| 2 | Apply SAP Note 2190195 – SUM known issues for your SUM version | SNOTE |  |
| 3 | Complete and import ALL open transport requests | SE10 / STMS |  |
| 4 | Lock transport system to prevent new imports during update | STMS → SE06 |  |
| 5 | Run ABAP Test Cockpit check – resolve all BLOCKER findings | ATC |  |
| 6 | Delete old application logs (SLG2), spool (SPAD), ABAP dumps (ST22) | SLG2 / SPAD / ST22 |  |
| 7 | Delete/deactivate $TMP objects in development systems | SE03 / SCOUR |  |
| 8 | Verify system is Unicode (mandatory for S/4HANA) | SE16N → SAPUNICOD |  |
| 9 | Check SM21 for critical errors – resolve before SUM | SM21 |  |
| 10 | Ensure no active ABAP dumps (ST22) before SUM start | ST22 |  |
| 11 | Perform full SAP system backup (HANA + filesystem) | HANA Cockpit / DB13 |  |
| 12 | Verify backup is restorable (test restore on sandbox) | HANA Cockpit |  |
| 13 | Check disk space: SUM needs 50+ GB free on /usr/sap and /hana/shared | df -h |  |
| 14 | Verify Java version (JAVA_HOME): min SAP JVM 8 | java -version |  |
| 15 | Notify all stakeholders of update schedule and expected downtime window | Change Management |  |

# 3. SUM Initialization & Configuration

## 3.1  Start SUM Web Interface

SUM operates through a web-based UI. Start the SUM process as the <sid>adm user:

# Switch to HANA / SAP admin user

su - <sid>adm

# Navigate to SUM directory

cd /usr/sap/<SID>/SUM/abap

# Start SUM

./SAPup MOD=UPGRADE

# OR for SPS update specifically:

./SAPup MOD=PATCH

# SUM outputs the access URL, for example:

# https://<hostname>:1128/lmsl/sumabap/<SID>/index.html

# Open the URL in a browser

# Default credentials: SAP client 000, user DDIC (or as configured)

📌 NOTE: SUM must be started as <sid>adm, NOT as root. The SUM process will run in the background — do not close the terminal session or it may interrupt the process. Use 'screen' or 'tmux' for resilience.

## 3.2  SUM — Initial Configuration Steps

| Step | SUM Screen / Phase | Action / Input Required |
| --- | --- | --- |
| 1 | Welcome / Start | Select: Support Package Update (SPS). Confirm SID and system details are correct. |
| 2 | Software Stack (Stack.xml) | Browse to STACK.XML generated by SAP Maintenance Planner. SUM reads target versions. |
| 3 | Software Packages Location | Point SUM to the download staging directory: /usr/sap/<SID>/SUM/download/ |
| 4 | Package Validation | SUM validates all downloaded packages against STACK.XML. Fix any missing packages. |
| 5 | System Access — ABAP | Enter SAP client (000), ABAP user (DDIC), and DDIC password for SUM to access the system. |
| 6 | System Access — OS | Enter <sid>adm OS user and password. SUM needs OS access for file operations. |
| 7 | Database Access | Enter HANA SYSTEM user and password (or ABAP DB schema user). SUM needs DB access for shadow operations. |
| 8 | Downtime Strategy | Select: Standard Downtime Minimization (recommended) OR Near-Zero Downtime (nZDT) if licensed. Standard is default. |
| 9 | Configuration Review | SUM displays all settings. Review and confirm. Click 'Next' to begin pre-checks. |

🔶 CAUTION: SUM saves its configuration and progress in /usr/sap/<SID>/SUM/abap/. NEVER delete this directory during an active SUM run. If SUM is interrupted, restart it from the same URL — it will resume from the last completed step.

## 3.3  SUM Silent / Automated Start (Optional)

For environments where interactive start is not preferred, SUM can be initiated with pre-defined parameters:

# Create SUM configuration input file

cat > /usr/sap/<SID>/SUM/abap/inifile.params << 'EOF'

NW_GetSidNoProfile.sid = <SID>

NW_readProfileDir.profileDir = /usr/sap/<SID>/SYS/profile

NW_GetMasterPassword.masterPwd = <MASTER_PASSWORD>

HDB_Schema_Check_Dialogs.schemaPassword = <SCHEMA_PW>

EOF

# Start SUM with parameter file

./SAPup MOD=PATCH INIFILE=/usr/sap/<SID>/SUM/abap/inifile.params

# Remove parameter file after SUM starts

rm -f /usr/sap/<SID>/SUM/abap/inifile.params

⚠ WARNING: Remove parameter files containing passwords immediately after SUM initialization. Never leave credentials in plain-text files.

# 4. SUM Pre-Checks Phase (Uptime)

The SUM pre-checks phase runs a comprehensive set of automated validations against the source system to identify any blockers or warnings before the actual update begins. This phase runs entirely in uptime — the system remains fully available to users.

## 4.1  SUM Automated Pre-Checks

SUM automatically executes the following pre-checks after initialization. Review each category carefully:

| Pre-Check Category | What SUM Checks | Severity if Failed |
| --- | --- | --- |
| System Prerequisites | OS version, kernel version, Java version, disk space, Unicode status | ERROR – must resolve before proceeding |
| SP/SPS Consistency | Current SP levels vs expected baseline; conflicting SP combinations | ERROR – cannot skip |
| Add-On Compatibility | Installed SAINT add-ons compatible with target SPS; conflicting patches | ERROR or WARNING |
| Custom Code (ATC) | ABAP syntax errors that would break after SPS import; removed function modules | ERROR if blockers exist |
| Simplification Items | Functional changes in target SPS that require pre-migration configuration | WARNING – review required |
| Open Customizing Tasks | Unfinished Customizing activities that SPS update requires to be complete | WARNING |
| Database Compatibility | HANA DB version compatibility with target SPS; JDBC driver versions | ERROR if incompatible |
| Transport Consistency | No open transports in import queue; no ERROR status imports | ERROR if queue not clear |
| Profile Parameters | Required instance/default profile parameters for SUM operation | SUM auto-updates profiles |
| System Resources | Available memory, work processes, background job slots for SUM execution | WARNING – may impact SUM speed |

## 4.2  Resolving Pre-Check Findings

SUM categorizes findings as ERROR (must fix), WARNING (must review and accept), or INFO (informational). Handle each:

| Finding Type | Action Required | Typical Resolution |
| --- | --- | --- |
| ERROR | Must be resolved — SUM will not proceed | Apply missing OSS notes (SNOTE); clear transport queue; resolve disk space; fix ATC blockers |
| WARNING | Review and either fix or explicitly accept in SUM UI | Read the SAP Note linked in the warning; accept if not applicable to your landscape |
| INFO | No action needed — informational only | Review for awareness; document any significant information items |

✔ TIP: If SUM reports an ERROR for a missing OSS Note, apply it via SNOTE while SUM is waiting on the pre-checks screen. SUM can re-run checks without restarting.

## 4.3  Pre-Check Resolution Checklist

| ✓ | Pre-Check Item | Owner | Done? |
| --- | --- | --- | --- |
| ☐ | All ERROR pre-checks resolved (no red items in SUM pre-check screen) | Basis |  |
| ☐ | All WARNING pre-checks reviewed and accepted or resolved | Basis |  |
| ☐ | ATC blockers from SUM code check resolved and transported | ABAP Dev |  |
| ☐ | Disk space warning resolved (50+ GB free on /usr/sap and /hana/shared) | Basis/Infra |  |
| ☐ | Missing OSS prerequisite notes applied via SNOTE | Basis |  |
| ☐ | Add-on conflict resolved (re-import compatible version or accept exclusion) | Basis |  |
| ☐ | Transport queue cleared – no pending imports | Basis |  |
| ☐ | Simplification item impact acknowledged and signed off by functional leads | Functional |  |
| ☐ | SUM pre-check screen shows ALL GREEN before clicking Next | Basis |  |

# 5. SUM Uptime Processing Phases

After pre-checks pass, SUM enters its main uptime processing phases. These are the longest parts of the update and run while the system is fully available to users. SUM works in the background on shadow schema and background queues without impacting production activity.

## 5.1  Package Extraction & Queue Generation

SUM extracts all downloaded SAR packages and generates its internal processing queue. This phase is automatic — no interaction needed except monitoring.

# Monitor SUM progress via web UI

# URL: https://<hostname>:1128/lmsl/sumabap/<SID>/index.html

# Monitor SUM log from OS in parallel

tail -f /usr/sap/<SID>/SUM/abap/log/SUMSTART.LOG

tail -f /usr/sap/<SID>/SUM/abap/log/SAPup_<SID>.log

# Monitor active SUM background work processes in SAP

# SM66 → filter by program 'RSUPGBTC*'

## 5.2  Shadow Repository Import (DDIC Activation)

SUM creates a shadow copy of the ABAP Dictionary (DDIC) and imports the new SPS objects into the shadow schema. Production DDIC remains unchanged during this phase.

| Sub-Phase | What Happens |
| --- | --- |
| SHADOW_IMPORT | New ABAP objects imported into shadow repository (not yet active in production) |
| SHADOW_DDIC | DDIC structures activated in shadow schema — new table definitions, fields, indexes created |
| SHADOW_ABAP | ABAP programs compiled against new DDIC in shadow — syntax and compatibility checked |
| MAIN_IMPORT | Production repository updated (uptime portion — non-critical objects only during this phase) |
| EU_IMPORT | Mass activation of ABAP programs in background using RSEUMOD jobs — high CPU normal |
| EU_SWITCH | Final switch from old to new software version — happens at DOWNTIME start |

📌 NOTE: During EU_IMPORT (mass ABAP activation), CPU usage on the application server will spike significantly. This is normal. SUM uses up to N-1 background work processes for parallel activation. Ensure other users are aware of potential system slowness during this phase.

## 5.3  Monitoring Uptime Phases

# Check active background jobs spawned by SUM

# SM37 → Job name: RSUPGBTC* OR RSBDCSUB*

# Monitor ABAP activation job progress

# SM37 → filter by program: RSEUMOD or RSUPGBTC

# Check SUM-specific log files

ls /usr/sap/<SID>/SUM/abap/log/

tail -100f /usr/sap/<SID>/SUM/abap/log/DDIC_<SID>.log

tail -100f /usr/sap/<SID>/SUM/abap/log/MAIN_<SID>.log

# Check for errors in SUM log

grep -i 'error\|failed\|abort' /usr/sap/<SID>/SUM/abap/log/*.log

## 5.4  Handle SUM Warnings During Uptime Phases

SUM may pause and request operator intervention during uptime phases. Common scenarios:

| SUM Pause Scenario | Resolution |
| --- | --- |
| Missing packages identified during queue validation | Download missing SAR from SAP Software Center; place in staging dir; SUM re-validates automatically |
| Conflicting add-on version detected | Check SAP Note for add-on SP compatibility; apply compatible SP or accept exclusion in SUM |
| ABAP syntax error in custom code found during shadow import | Fix custom code in SE38; transport to the system; SUM can re-import without restart |
| SUM background jobs failing repeatedly | Check SM37 job logs; SM21 for errors; apply relevant OSS note; restart stuck SUM phase via SUM UI |
| DB space warning during shadow import | Extend HANA disk or free space in /hana/data; SUM will automatically retry when space available |
| SUM shows 'Wait for dialog' status for extended time | Log into SUM UI and respond to any pending questions; check for timeouts in SUM log |

# 6. Downtime Execution

The downtime phase is the critical window where the system is locked and unavailable to users. SUM completes the final import steps, activates the new software version, and runs mandatory post-import programs. The goal is to execute this phase as fast as possible within the agreed maintenance window.

## 6.1  Pre-Downtime Preparation Checklist

| ✓ | Task | Owner | Done? |
| --- | --- | --- | --- |
| ☐ | Confirm all SUM uptime phases completed (green in SUM UI) before starting downtime | Basis |  |
| ☐ | Send final user notification: 'System going down for maintenance at <TIME>' | Basis |  |
| ☐ | Lock all SAP logons via SM01 | Basis |  |
| ☐ | Cancel or reschedule all background jobs for the downtime window | Basis |  |
| ☐ | Verify no active users in SM04 / AL08 (or agreed minimum) | Basis |  |
| ☐ | Verify no active update records in SM13 | Basis |  |
| ☐ | Confirm HANA database backup completed within last 24 hours | DBA |  |
| ☐ | Take OS-level snapshot / GCP VM snapshot as rollback safety net | Infra |  |
| ☐ | Inform stakeholders downtime window is starting | Delivery |  |
| ☐ | Record exact downtime start time | Basis |  |

## 6.2  Initiate Downtime in SUM

When all pre-downtime preparation is complete, proceed to start the downtime phase in the SUM UI:

- In the SUM web interface, navigate to the 'Downtime' phase screen

- SUM will show a summary of remaining steps and estimated duration

- Click 'Start Downtime' — SUM will automatically lock the SAP system

- SUM stops user dialog and batch access (independent of SM01 — SUM has its own lock)

- SUM stops relevant SAP services if required (ICM, message server)

🔑 KEY STEP: Once 'Start Downtime' is clicked in SUM, the process is automated. Do NOT stop SUM, restart services manually, or interfere with the process unless instructed by SAP Support.

## 6.3  SUM Downtime Phase Steps (Automated)

| Step | SUM Sub-Phase | Description |
| --- | --- | --- |
| 1 | EU_SWITCH_PRE | Pre-switchover checks; SUM verifies shadow repo is complete and consistent |
| 2 | LOCK_EUMOD | SAP system locked; all dialog and batch access blocked |
| 3 | EU_SWITCH | Software version switch executed — new S/4HANA SPS becomes active version |
| 4 | MAIN_IMPORT_DT | Final delta import of objects that could not be imported during uptime |
| 5 | DDIC_IMPORT_DT | Final DDIC activations in production (table extensions, new indexes, etc.) |
| 6 | MAIN_NEWBAS | New basis objects activated; kernel and runtime components updated |
| 7 | TABCONVERT | Table conversions for structural changes (new columns, data type changes) |
| 8 | EU_IMPORT_DT | Final ABAP program activations that require downtime (restricted set) |
| 9 | XPRA_EXECUTION | Post-import conversion programs (XPRAs) run — data migration within ABAP |
| 10 | SPDD_SPAU_AUTO | Automatic resolution of modification adjustments (SPDD/SPAU) where possible |
| 11 | SYSTEM_UNLOCK | SAP system unlocked; access restored for testing team |
| 12 | POST_PROCESSING | SUM-initiated post-processing jobs run; system handover |

## 6.4  Monitor Downtime Execution

# Monitor SUM downtime log in real time

tail -200f /usr/sap/<SID>/SUM/abap/log/SAPup_<SID>.log

# Watch XPRA conversion programs

tail -f /usr/sap/<SID>/SUM/abap/log/XPRA*.log

# Monitor table conversions

tail -f /usr/sap/<SID>/SUM/abap/log/TABCONVERT*.log

# Check for errors

grep -i 'return code [^0]\|ERROR\|FAILED\|ABORT' \

/usr/sap/<SID>/SUM/abap/log/SAPup_<SID>.log | tail -50

# Monitor HANA TABCONVERT space (table conversions can require significant space)

hdbsql -u SYSTEM -p <pw> \

'SELECT FREE_PHYSICAL_MEMORY, ALLOCATION_LIMIT FROM SYS.M_HOST_RESOURCE_UTILIZATION'

# 7. Post-Update Tasks

After SUM completes the downtime phase and unlocks the system, a comprehensive set of post-update activities must be performed before returning the system to users. These tasks validate update success, resolve modification adjustments, and ensure system stability.

## 7.1  Immediate Post-SUM System Checks

| # | Verification Task | Transaction | Pass? |
| --- | --- | --- | --- |
| 1 | Verify new SPS level installed correctly | SE16N → CVERS OR SM51 |  |
| 2 | SUM final status shows 'Completed Successfully' | SUM Web UI |  |
| 3 | All SAP work processes GREEN | SM50 / SM66 |  |
| 4 | No new ABAP dumps since update | ST22 – last 2 hours |  |
| 5 | No critical errors in system log | SM21 – last 2 hours |  |
| 6 | HANA DB connection active; DBACOCKPIT accessible | DBACOCKPIT / ST04 |  |
| 7 | ICM running and HTTP/HTTPS services active | SMICM → Services |  |
| 8 | Message server and enqueue server running | SM51 → Server Details |  |
| 9 | Batch job framework active | SM65 |  |
| 10 | RFC destinations operational | SM59 → Test connections |  |
| 11 | SUM post-processing jobs completed (SM37 – RSUPGBTC jobs finished) | SM37 |  |
| 12 | Check SICK transaction (System Consistency Check) | SICK |  |

## 7.2  SPDD / SPAU — Modification Adjustment

SPDD and SPAU are critical post-update steps that handle SAP object modifications that were overwritten by the SPS update. These must be processed before system release to users.

| Transaction | Handles | When & How |
| --- | --- | --- |
| SPDD | DDIC modifications (table/structure field changes, domain modifications) | Run IMMEDIATELY after downtime ends; before starting ABAP. Reset or re-adjust custom DDIC modifications. |
| SPAU | ABAP program modifications (includes, forms, function modules, exits) | Run after SPDD; review each modified object and decide: Reset to SAP Standard, or Re-adjust your modification. |

# SPDD — DDIC Modification Adjustment

# Transaction: SPDD

# Steps:

# 1. Execute SPDD → review list of modified DDIC objects

# 2. For each: choose 'Reset to Original' (SAP) or 'Adjust' (keep custom)

# 3. Activate all adjusted objects

# 4. Confirm all SPDD entries resolved (empty SPDD list = complete)

# SPAU — ABAP Modification Adjustment

# Transaction: SPAU

# Steps:

# 1. Execute SPAU → shows all modified SAP programs

# 2. Prioritize: first handle programs causing ABAP dumps

# 3. For each: 'Reset' (lose modification) or 'Adjust' (manually merge changes)

# 4. Use SCI (Code Inspector) to validate adjusted objects

# 5. Activate and transport adjusted objects

⚠ WARNING: SPDD must be processed BEFORE SPAU. Unresolved SPDD objects can cause cascade failures in SPAU. Never skip SPDD/SPAU — unresolved modifications cause runtime errors, incorrect business behavior, and upgrade issues in future updates.

## 7.3  Post-Update Mandatory OSS Notes & Patches

After every SPS update, review and apply SAP Notes that are specific to the new SPS level:

- Check SAP Note for your target SPS (e.g., SAP Note 3045229 for S/4HANA 2023 SPS02 corrections)

- Apply all HOT NEWS notes (priority VERY HIGH) for the new SPS

- Apply security notes from the latest SAP Security Patch Day (released monthly)

- Review SUM log for any notes SUM identified but could not auto-apply

# Apply recommended post-update notes via SNOTE

# Transaction: SNOTE

# → Download → Apply (in sequence if dependencies exist)

# → Activate in SE80 or via SNOTE activation

## 7.4  Restart Background Jobs

# Review and restart background jobs in staged sequence

# Start with critical infrastructure jobs first:

# 1. BASIS infrastructure jobs

# SM36 → Enable: SAP_REORG_JOBS, SAP_COLLECTOR_FOR_PERF,

#              SAP_CCMS_MONI_BATCH_DP

# 2. Finance close-related jobs (if period-end not in progress)

# Check SM37 → release jobs in planned order

# 3. Monitor first run of each job

# SM37 → watch for ABAP dumps or abnormal terminations

## 7.5  Functional Smoke Tests

| Module / Area | Test Transaction | Expected Result |
| --- | --- | --- |
| Basis / System | SM51, SM50, SICK, SMICM | All servers active; all processes GREEN; no critical alerts |
| ABAP Development | SE38 → run RSPARAM | Parameters displayed; no dump |
| Finance (FI) | FB01 → park test document | Document parked without error; ACDOCA entry created |
| Controlling (CO) | KSB1 → display cost center report | Report displays without dump |
| Materials Management | ME21N → create test PO | PO created; number range working |
| Sales & Distribution | VA01 → create test sales order | Order created; pricing determined |
| Production Planning | MD04 → MRP stock requirements list | List displayed; no errors |
| SAP Fiori | Open Fiori Launchpad in browser | Apps load correctly; tiles visible |
| Batch Processing | SM36 → schedule test job | Job finishes with status: Finished |
| Printing / Spool | SP01 → output a spool request | Output processed; no spool errors |
| Workflow | SWI1 → check workitem list | Workitems visible; workflow engine running |
| Interfaces / RFC | SM59 → test all active RFC destinations | All connections: OK |

# 8. SUM Cleanup & System Finalization

## 8.1  Complete SUM Finalization

After all post-update checks pass, finalize the SUM run in the web interface:

- In SUM Web UI, navigate to the final 'Finalization' screen

- Review the SUM update summary report

- Click 'Finalize' — SUM performs its final cleanup and marks the update as complete

- SUM archives its log files to /usr/sap/<SID>/SUM/abap/log/archive/

- SUM records the update in the system history (SM31 → SYSUPG)

## 8.2  Post-SUM Disk Cleanup

# Archive or remove SUM download staging directory (after update confirmed good)

# Option 1: Archive to slow storage

tar -czf /hana/shared/<SID>/sum_archive_$(date +%Y%m%d).tar.gz \

/usr/sap/<SID>/SUM/download/

# Option 2: Delete staging area (only if confident update successful)

rm -rf /usr/sap/<SID>/SUM/download/

# Remove SUM temp directory

rm -rf /usr/sap/<SID>/SUM/abap/tmp/

# Check recovered disk space

df -h /usr/sap /hana/shared

## 8.3  Unlock Transport System

# Re-enable transport system for new changes

# Transaction: STMS → SE06 → Set system to 'Production' mode

# OR

# SE03 → Settings → unlock transport system

# Verify transport routes are active

# STMS → Transport Routes → Check configuration

## 8.4  Update System Documentation

| ✓ | Documentation Task | Owner | Done? |
| --- | --- | --- | --- |
| ☐ | Record new SPS level in system inventory / landscape documentation | Basis |  |
| ☐ | Update runbooks with new SPS version and any configuration changes | Basis |  |
| ☐ | Archive SUM summary report to project documentation | Basis |  |
| ☐ | Document SPDD/SPAU objects that were reset to SAP standard | ABAP Dev |  |
| ☐ | Update SAP LMDB / Solution Manager with new SPS version | Basis |  |
| ☐ | Close change request / maintenance ticket | Delivery |  |
| ☐ | Send completion notification to all stakeholders | Delivery |  |

# 9. Rollback Procedure

Unlike a kernel update, an SPS update via SUM cannot be cleanly reversed at the ABAP level once the EU_SWITCH (software version switch) step is complete. The only reliable rollback for an SPS update is restoring from the pre-update system backup. This reinforces the critical importance of a verified backup and OS-level snapshot before every SPS update.

⚠ WARNING: SPS rollback is a significant operation. It restores the system to its pre-update state, losing any transactions processed since the backup. Establish a go/no-go decision point with stakeholders before starting the downtime phase — rolling back from a partially completed SPS update is far more complex than not starting.

## 9.1  Rollback Decision Framework

| Scenario | Rollback Feasibility | Action |
| --- | --- | --- |
| SUM fails during pre-checks (uptime) | Easy – No system change yet | Stop SUM; fix issue; restart SUM. No rollback needed. |
| SUM fails during shadow import (uptime) | Easy – Shadow schema only | Stop SUM; fix issue; restart SUM from last step. Production untouched. |
| SUM fails before EU_SWITCH (downtime start) | Easy – DB not yet switched | SUM can retry from last step; no rollback of production needed. |
| SUM fails during EU_SWITCH or MAIN_IMPORT_DT | Possible – restore from backup | Restore OS snapshot + HANA backup; re-validate; re-plan update. |
| SPS update complete but critical functional issue | Difficult – data may exist | Restore from backup (loses post-go-live transactions); or fix via hotfix/note. |
| System unstable after SPS update | Possible – time-limited | Restore backup within agreed RPO window; engage SAP Support urgently. |

## 9.2  Rollback from OS Snapshot (GCP)

# 1. Stop all SAP instances immediately

su - <sid>adm && stopsap ALL

# 2. Stop SAP HANA database

su - <sid>adm && HDB stop

# 3. Restore OS snapshot (GCP) — for boot disk

gcloud compute instances stop <sap-app-server-vm> --zone=<ZONE>

gcloud compute disks restore-snapshot <boot-disk> \

--snapshot=<pre-sps-update-snapshot> --zone=<ZONE>

gcloud compute instances start <sap-app-server-vm> --zone=<ZONE>

# 4. Restore HANA database from pre-update backup

# Login to HANA Studio or hdbsql and run recovery:

hdbsql -u SYSTEM -p <pw> \

"RECOVER DATABASE UNTIL TIMESTAMP '<pre-update-timestamp>'"

# OR use HANA Cockpit Recovery Wizard

# 5. Start SAP instances and verify pre-update SPS level

startsap ALL

# SE16N → CVERS — must show old SPS level

# 10. Special Scenarios

## 10.1  Near-Zero Downtime (nZDT) Option

SAP SUM 2.0 offers a Near-Zero Downtime (nZDT) option for SPS updates that reduces the downtime window from hours to minutes. The nZDT approach uses HANA System Replication shadow operations to perform the update with minimal production lock.

| nZDT Aspect | Details |
| --- | --- |
| SAP Note Reference | SAP Note 2578458 — nZDT with SUM 2.0 for S/4HANA SPS updates |
| License Requirement | Requires SAP S/4HANA Cloud or specific on-premise contract — verify license |
| Additional Requirement | HANA System Replication must be configured; separate HANA secondary for shadow |
| Downtime Reduction | Typical downtime reduced from 4–8 hours to 15–45 minutes |
| Complexity | Significantly more complex to configure and execute vs standard SUM |
| When to Use | Mission-critical systems requiring 24/7 availability; production with <1hr downtime SLA |

## 10.2  SPS Update on Distributed Landscape

In a distributed S/4HANA landscape (multiple application server hosts), SUM must be started on the PRIMARY APPLICATION SERVER (PAS) host. SUM will coordinate with all AAS instances.

- Run SUM exclusively on the PAS host — AAS instances are updated automatically

- Ensure all AAS hosts have the same kernel version as PAS before starting SUM

- ASCS/ERS instances (Message Server, Enqueue) are updated by SUM from PAS

- After SUM completes, manually restart AAS instances if SUM did not restart them

- Verify SPS level via SM51 on EACH server instance — all must show same level

## 10.3  SPS Update on PCE / NS2 Cloud Environments

SAP S/4HANA Cloud Private Edition (PCE) and NS2 environments have additional governance requirements for SPS updates:

- Raise a Change Request via SAP Cloud ALM before scheduling any SPS update

- Validate target SPS is in the SAP-approved PCE update catalog for your contract

- PCE updates may require SAP-managed hands-on execution — confirm co-managed scope

- NS2 environments may have additional US Government compliance steps (FISMA/FedRAMP)

- Post-update validation must include Cloud ALM health check dashboard sign-off

## 10.4  ABAP + HANA Combined Update Window

Many teams combine the SAP kernel update and HANA DB update with the SPS update in a single maintenance window to minimize total downtime events:

| Step | Activity | Notes |
| --- | --- | --- |
| T-1 week | Download all packages: ABAP SPs, Kernel, HANA revision | Use Maintenance Planner for consistent stack |
| T-0 Uptime | Run SUM uptime phases (shadow import, DDIC) | System running; lasts 4–8 hours depending on size |
| T-0 Downtime | SUM downtime phase (EU_SWITCH, XPRA) | System locked; 2–4 hours typical |
| T-0 Post | Kernel replacement (OS-level cp) on all hosts | 15 min; kernel update takes advantage of existing downtime |
| T-0 Post | HANA revision update via HDBLCM (if HANA update also needed) | 30–60 min; combines into same window |
| T-0 Final | Start all instances; full verification | Allow 60–90 min for complete smoke testing |

# 11. Troubleshooting

## 11.1  Common SUM Issues & Resolution

| Issue / Symptom | Root Cause | Resolution |
| --- | --- | --- |
| SUM fails: 'STACK.XML not found or invalid' | Wrong STACK.XML from different SID or SPS target | Re-run Maintenance Planner for THIS system's SID; download new STACK.XML |
| SUM fails: 'Insufficient disk space' | /usr/sap or /hana/shared too full | Free space: remove old SUM archives, application logs, $TMP objects; need 50+ GB |
| SUM fails: 'Open transports in queue' | Pending transport imports not cleared | STMS → import all pending transports or remove from queue; lock transport system |
| SUM pre-check: 'Add-on version incompatible' | Installed add-on not compatible with target SPS | Check SAP add-on compatibility matrix; apply compatible add-on SP or contact vendor |
| SUM shadow import fails for specific object | Custom code modification conflict | Check SUM log for object name; fix in SE38 and transport; SUM can retry import |
| XPRA program fails during downtime | Data inconsistency or custom modification conflict | Check /usr/sap/<SID>/SUM/abap/log/XPRA*.log; apply SAP Note for specific XPRA |
| SUM appears stuck on same step for 2+ hours | Deadlock, background job failure, or DB issue | Check SM37 for stuck SUM jobs; check SM12 for enqueue locks; check HANA alerts |
| TABCONVERT fails: 'Table conversion timeout' | Large table conversion exceeding SUM timeout | Increase SUM timeout in SUM UI; or pre-run table conversion before downtime |
| System unstable after SUM: work process restarts | Unresolved SPDD/SPAU modification | Run SPDD and SPAU immediately; activate adjusted objects; restart application |
| AAS instance shows old SPS level after update | AAS not restarted by SUM or symlink not updated | Manually restart AAS; verify kernel symlink points to correct new version |
| ABAP dump: 'Class or method not found' after SPS | SE80 object not activated or SPAU not complete | Run SPAU; activate object in SE80; or apply SAP Note for specific dump |
| SUM cannot connect to HANA (DB access error) | HANA password changed or ABAP schema locked | Verify HANA SYSTEM user PW; check ABAP schema user lock status in HANA Cockpit |

## 11.2  Key Log Files for Troubleshooting

| Log File Path | What to Check |
| --- | --- |
| /usr/sap/<SID>/SUM/abap/log/SAPup_<SID>.log | Main SUM execution log — start here for any SUM issue |
| /usr/sap/<SID>/SUM/abap/log/SUMSTART.LOG | SUM startup and configuration log |
| /usr/sap/<SID>/SUM/abap/log/DDIC_<SID>.log | DDIC activation log — for shadow import and SPDD issues |
| /usr/sap/<SID>/SUM/abap/log/MAIN_<SID>.log | Main import log — for SP import errors |
| /usr/sap/<SID>/SUM/abap/log/XPRA_<SID>.log | XPRA conversion program logs — post-import data migrations |
| /usr/sap/<SID>/SUM/abap/log/TABCONVERT*.log | Table conversion logs — structural changes, timeouts |
| /usr/sap/<SID>/SUM/abap/log/CHECKS_<SID>.log | Pre-check results log — details of ERROR/WARNING findings |
| /usr/sap/<SID>/D<NR>/work/dev_disp | Application server dispatcher log — startup after SPS |
| /usr/sap/<SID>/D<NR>/work/dev_w0 | Work process log — ABAP dump details |
| /var/log/messages OR journalctl | OS system log — disk/memory/network events during SUM |

# 12. Master SPS Update Checklist

This consolidated sign-off checklist covers all phases of an SAP S/4HANA SPS update. Use as the primary execution and handover record for every SPS update event.

| ✓ | Phase | Task | Owner | Done |
| --- | --- | --- | --- | --- |
| ☐ | PRE | Generate target stack XML from SAP Maintenance Planner | Basis |  |
| ☐ | PRE | Download all packages per Maintenance Planner basket (ABAP SPs, Kernel, HANA Client) | Basis |  |
| ☐ | PRE | Verify checksums of all downloaded SAR/ZIP files | Basis |  |
| ☐ | PRE | Verify current SPS level and confirm target SPS is correct | Basis |  |
| ☐ | PRE | Check installed add-on compatibility with target SPS (SAINT) | Basis |  |
| ☐ | PRE | Apply all mandatory prerequisite OSS Notes (SAP Note 2399707, 2190195) | Basis |  |
| ☐ | PRE | Run ATC custom code checks; resolve all BLOCKER findings | ABAP Dev |  |
| ☐ | PRE | Release and import all open transports; lock transport system | Basis |  |
| ☐ | PRE | Delete old application logs (SLG2), spool (SPAD), ABAP dumps (ST22) | Basis |  |
| ☐ | PRE | Verify disk space: 50+ GB free on /usr/sap and /hana/shared | Basis/Infra |  |
| ☐ | PRE | Verify SAP JVM / JAVA_HOME configured for SUM | Basis |  |
| ☐ | PRE | Extract SUM 2.0 to /usr/sap/<SID>/SUM/; verify SUM version | Basis |  |
| ☐ | PRE | Take full HANA backup (SYSTEMDB + all tenants); verify catalog | DBA |  |
| ☐ | PRE | Take OS-level VM snapshot (GCP) as rollback safety net | Infra |  |
| ☐ | PRE | Confirm change request approved with agreed maintenance window | Delivery |  |
| ☐ | PRE | Send maintenance pre-notification to all stakeholders | Delivery |  |
| ☐ | UPT | Start SUM: ./SAPup MOD=PATCH as <sid>adm | Basis |  |
| ☐ | UPT | Configure SUM: provide STACK.XML, download dir, ABAP user, OS user, DB credentials | Basis |  |
| ☐ | UPT | SUM pre-checks: resolve ALL ERROR findings before proceeding | Basis |  |
| ☐ | UPT | SUM pre-checks: review and accept or fix all WARNING findings | Basis |  |
| ☐ | UPT | ATC blockers from SUM code check resolved and transported | ABAP Dev |  |
| ☐ | UPT | Functional leads sign off on Simplification Item warnings | Functional |  |
| ☐ | UPT | SUM package extraction and queue generation completed | Basis |  |
| ☐ | UPT | SUM shadow repository import (SHADOW_IMPORT) completed | Basis |  |
| ☐ | UPT | SUM DDIC activation in shadow (SHADOW_DDIC) completed | Basis |  |
| ☐ | UPT | SUM ABAP compilation in shadow (SHADOW_ABAP) completed | Basis |  |
| ☐ | UPT | SUM main import uptime portion (MAIN_IMPORT) completed | Basis |  |
| ☐ | UPT | SUM EU_IMPORT activation jobs (RSEUMOD) completed in SM37 | Basis |  |
| ☐ | UPT | SUM reports 'Ready for Downtime' status in web UI | Basis |  |
| ☐ | DWN | Final user lockout: SM01 + SM02 system message sent | Basis |  |
| ☐ | DWN | Confirm no active users (SM04 / AL08 clear) | Basis |  |
| ☐ | DWN | Confirm no active background jobs in SM37 | Basis |  |
| ☐ | DWN | Record exact downtime start time | Basis |  |
| ☐ | DWN | Click 'Start Downtime' in SUM UI | Basis |  |
| ☐ | DWN | SUM EU_SWITCH completed (version switch executed) | Basis |  |
| ☐ | DWN | SUM TABCONVERT completed (all table conversions done) | Basis |  |
| ☐ | DWN | SUM XPRA_EXECUTION completed (all conversion programs run) | Basis |  |
| ☐ | DWN | SUM reports downtime phase completed; system unlocked | Basis |  |
| ☐ | POST | Verify new SPS level: SE16N → CVERS shows target SPS | Basis |  |
| ☐ | POST | SUM finalization completed; summary report reviewed | Basis |  |
| ☐ | POST | SPDD executed and all entries resolved | ABAP Dev |  |
| ☐ | POST | SPAU executed and all entries resolved or accepted | ABAP Dev |  |
| ☐ | POST | All SAP work processes GREEN (SM50 / SM66) | Basis |  |
| ☐ | POST | No new ABAP dumps since SPS update (ST22) | Basis |  |
| ☐ | POST | No critical errors in SM21 system log since update | Basis |  |
| ☐ | POST | SICK transaction — all checks passed | Basis |  |
| ☐ | POST | Mandatory post-SPS OSS notes applied (SNOTE) | Basis |  |
| ☐ | POST | Background jobs restarted in staged sequence | Basis |  |
| ☐ | POST | RFC connections verified (SM59 → test all) | Basis |  |
| ☐ | POST | Functional smoke tests passed (FI, MM, SD, CO, Fiori) | Functional |  |
| ☐ | POST | Transport system unlocked | Basis |  |
| ☐ | POST | SUM download staging area archived / cleaned up | Basis |  |
| ☐ | POST | System documentation and LMDB updated with new SPS level | Basis |  |
| ☐ | POST | Maintenance ticket closed; completion notification sent | Delivery |  |

📘 REFERENCE: Key SAP Notes: 2502552 (SUM Update Guide), 2209025 (SUM 2.0 Prerequisites), 2190195 (SUM Known Issues), 2399707 (SUM Prerequisite Notes), 2578458 (nZDT Option), 2861952 (S/4HANA 2023 Recommended Stack), 3045229 (S/4HANA 2023 Corrections), 2180923 (Simplification Items), 2936831 (ATC for SPS).